## Product Backlog
Product Name: | MICE Manager | [5 empty] | Complete Fields in Green!!!
Team ID:
| Team Member Name |  |  |  |  | Initials | Student ID
Required | Nishad Aherrao |  |  |  |  | NSA | 1001351291
Sprint # | Remaining | Completed This Sprint |  |  | Comment
0 | 37 |  |  | Total | Total number of features (in column H)
1 | 34 | 3 |  | 1 | Total features left at the end of Sprint #1
2 | 31 | 3 |  | 2 | Total features left at the end of Sprint #2
3 | 25 | 6 |  | 3 | ...and so on
4 | 21 | 4
5 | 16 | 5
6 | 16 | 0
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority | Required | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
CF | 1 | 1 | 13 |  | Finished in Sprint 1 | Manager | Create a new ice cream flavor | Stock and sell dairy products | picture not yet required, just test the classes here w/o GUI
CC | 2 | 1 | 5 |  | Finished in Sprint 1 | Manager | Create a new container | Stock and sell dairy products | Picture not yet required
CT | 3 | 1 | 5 |  | Finished in Sprint 1 | Manager | Create a new topping | Stock and sell better dairy products | Picture not yet required
GUI | 4 | 2 | 8 |  | Finished in Sprint 2 | Manager | Use a GUI instead of a terminal | Reduce training costs | This is the main window, with menu bar, tool bar, and optionally status bar
IGUI | 5 | 2 | 13 |  | Finished in Sprint 2 | Manager | Use dialogs to create items | Reduce training costs | One dialog should server for all items with minor variations
CS | 6 | 2 | 8 |  | Finished in Sprint 2 | Server | Create a serving of ice cream in a container with toppings | Create dairy products to sell | Pick a container, 1-N scoop flavors, and 0-N toppings via one or more dialogs, instance a serving object, and push on a vector
PS | 7 | 3 | 5 |  | Finished in Sprint 3 | Customer | Show the components of a serving (container, scoops, and toppings) for verification | Ensure my order was taken correctly | This is effectively a to_string method to a dialog with confirm or start over buttons
CTM | 8 | 3 | 3 |  | Finished in Sprint 3 | Manager | Create a new server | Staff the emporium
CB | 9 | 3 | 2 |  | Finished in Sprint 3 | Server | Create a new beloved customer | Keep track of our customers
CO | 10 | 3 | 13 |  | Finished in Sprint 3 | Server | Create an order of many servings of ice cream | Serve everyone in a customer party
CSB | 11 | 3 | 1 |  | Finished in Sprint 3 | Customer | Create a serving of ice cream in a container with toppings | Self-order and not have to deal with people | This just enables the Customer role to do what the Server can do in defining a serving…
COB | 12 | 3 | 1 |  | Finished in Sprint 3 | Customer | Create an order of many servings of ice cream | Self-order and not have to deal with people | ...and order
CE | 13 | 4 | 5 |  | Finished in Sprint 4 | Manager | Create an emporium that stocks items and maintains a cash register | Manage the emporium | This includes item stocks, server and customer lists, and the cash register
MST | 14 | 4 | 8 |  | Finished in Sprint 4 | Manager | Manage the state of each order (unfilled -> filled -> paid, or unfilled -> canceled) | Ensure each order is filled and payment collected
SAVD | 15 | 4 | 8 |  | Finished in Sprint 4 | Manager | Save all data to a default file | Ensure our data isn’t lost
LOAD | 16 | 4 | 5 |  | Finished in Sprint 4 | Manager | Load data from a default file | Ensure our data isn’t lost
POS | 17 | 5 | 5 |  | Finished in Sprint 5 | Server | Show the servings in an order for the servers (what to prepare) | Know what to put into each serving in an order | This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
POC | 18 | 5 | 5 |  | Finished in Sprint 5 | Customer | Show the servings in an order for the customer (what was ordered / how much it costs) | Verify that my order was taken correctly and see the price | This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
PIX | 19 |  | 21 |  | Finished in Sprint 5 | Customer | Add and display pictures for each item (container, ice cream flavor, and topping) | Better understand the menu
CM | 20 |  | 3 |  | Finished in Sprint 5 | Owner | Create a new manager | Delegate management tasks to a pro
P&L | 21 |  | 8 |  | Finished in Sprint 5 | Manager | Add a Profit & Loss statement, showing all income, expenses, and total profit | Ensure that we’re making a profit and thus avoid bankruptcy
RI | 22 |  | 5 |  |  | Manager | Display an Inventory Report, listing every item and the quantity in stock | Ensure we don’t run out of any product and thus disappoint our customers
RTM | 23 |  | 8 |  |  | Manager | Display a Server Report, listing all info about each server including # of orders served | Better manage our team and reward productive team members
ETMS | 24 |  | 8 |  |  | Manager | Change a server salary | Offer promotions and pay bumps to motivate our team members
AI | 25 |  | 8 |  |  | Server | Restock items (ice cream flavor, container, and topping) | Ensure we can fill every order
RO | 26 |  | 8 |  |  | Manager | Create an Order Report, showing all pending orders (unfilled and filled but unpaid) | Better manage our production process
RB | 27 |  | 5 |  |  | Manager | Display a Customer Report, listing all info about each customer | Better attract repeat customers and handle complaints
EF | 28 |  | 8 |  |  | Manager | Edit an ice cream flavor | Improve our data and keep it synced to reality
EC | 29 |  | 8 |  |  | Manager | Edit a container | Improve our data and keep it synced to reality
ET | 30 |  | 8 |  |  | Manager | Edit a new topping | Improve our data and keep it synced to reality
ROA | 31 |  | 3 |  |  | Manager | Add Order Report option to show completed as well as pending orders | Review our order history seeking patterns to understand how to improve efficiency and profit
SALL | 32 |  | 5 |  |  | Owner | Save all data to a specified file | Franchise my company
LALL | 33 |  | 5 |  |  | Owner | Load data from a specified file | Franchise my company
CENEW | 34 |  | 13 |  |  | Owner | Create a new franchise | Franchise my company
XI | 35 |  | 21 |  |  | Manager | Retire an item (no longer enable its selection for a new order, but keep in reports) | Remove items no longer offered from the menu
XT | 36 |  | 13 |  |  | Manager | Suspend a server (no longer allow their selection for an order or restock, but keep in reports) | Remove team members who aren’t currently active from our drop-down lists (except reports)
XXT | 37 |  | 5 |  |  | Manager | Restore a server | Add a former team member tack into service

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2018-04-12 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2018-04-19
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 6
Day 1 Left | 6 | 0
Day 2 Left | 6 | 0
Day 3 Left | 5 | 1
Day 4 Left | 5 | 0
Day 5 Left | 3 | 2
Day 6 Left | 2 | 1
Day 7 Left | 0 | 2
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | PS |  | serving components | Completed Day 3
2 | CTM |  | Server new create | Completed Day 5
3 | CB |  | Customer new create | Completed Day 5
4 | CO |  | order | Completed Day 6
5 | CSB |  | Serving with all topp cont and scoop | Completed Day 7
6 | COB |  | order of many serving | Completed Day 7
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2018-03-29 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2018-04-05
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 12
Day 1 Left | 10 | 2
Day 2 Left | 7 | 3
Day 3 Left | 5 | 2
Day 4 Left | 3 | 2
Day 5 Left | 3 | 0
Day 6 Left | 0 | 3
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CF |  | Base Class Created | Completed Day 1
2 | CF |  | Item.cpp abstract class | Completed Day 1
3 | CF |  | First Derived Class Container .h/.cpp | Completed Day 2
4 | CF |  | Second Derived Class Scoop .h/.cpp | Completed Day 2
5 | CC |  | Third Derived Class Toppings .h/.cpp | Completed Day 2
6 | CC |  | Emporium class for multiple instances | Completed Day 3
7 | CT |  | Emporium.cpp created | Completed Day 3
8 | CT |  | View Class for MVC | Completed Day 4
9 | CE |  | View.cpp completed | Completed Day 4
10 | CE |  | Controller class for MVC | Completed Day 6
11 | CF |  | Controller.cpp completed | Completed Day 6
12 | CF |  | Main and other remaining adjustments | Completed Day 6
13 | CF
14 | CF
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2018-04-05 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2018-04-12
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 20
Day 1 Left | 20 | 0
Day 2 Left | 20 | 0
Day 3 Left | 19 | 1
Day 4 Left | 12 | 7
Day 5 Left | 9 | 3
Day 6 Left | 1 | 8
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | GUI |  | Create a main window (menu and tool bars) | Completed Day 3 | Baseline from Nim
2 | IGUI |  | Add item vectors to main window class | Completed Day 4
3 | IGUI |  | Add Mainwin::create_item dialog – select item type | Completed Day 4
4 | IGUI |  | Add Mainwin::create_item dialog – create item | Completed Day 4
5 | CS |  | Create Serving class | Completed Day 4
6 | CS |  | Create Mainwin::select_container() method | Completed Day 4
7 | CS |  | Create Mainwin::select_scoop() method | Completed Day 4
8 | CS |  | Create Mainwin::select_topping() method | Completed Day 4
9 | CS |  | Add Mainwin::create_serving() private method | Completed Day 5
10 | CS |  | Add operator<< for Item (use POLYMORPHISM) | Completed Day 5
11 | CS |  | Update regression tests to support operator<< | Completed Day 5
12 | CS |  | Create Mainwin::on_create_order_click() (but create serving) | Completed Day 6
13 | CS |  | Add operator<< for Serving | Completed Day 6
14 | CS |  | Show created serving temporarily on STDOUT | Completed Day 6
15 | CS |  | Add (temporary) Mainwin::_servings vector and push to it | Completed Day 6
16 | CS |  | Find icons | Completed Day 6
17 | CS |  | Find a logo | Completed Day 6
18 | CS |  | Create Help > About dialog to credit icon and logo authors | Completed Day 6 | Baseline from CSE1325 Paint
19 | CS |  | Add toolbar icons for Create Item and Create Order | Completed Day 6
20 | CS |  | Update class diagram
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2018-04-19 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2018-04-26
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 4
Day 1 Left | 4 | 0
Day 2 Left | 4 | 0
Day 3 Left | 4 | 0
Day 4 Left | 4 | 0
Day 5 Left | 4 | 0
Day 6 Left | 2 | 2
Day 7 Left | 0 | 2
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CE |  | emporium cash salary manage | Completed Day 6
2 | MST |  | state of order | Completed Day 6
3 | LOAD |  | load a saved emporium | Completed Day 7
4 | SAVD |  | save emporium | Completed Day 7
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2018-04-26 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2018-05-03
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 5
Day 1 Left | 5 | 0
Day 2 Left | 3 | 2
Day 3 Left | 3 | 0
Day 4 Left | 3 | 0
Day 5 Left | 3 | 0
Day 6 Left | 1 | 2
Day 7 Left | 0 | 1
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | POS |  | Show servings of order to Server | Completed Day 2
2 | POC |  | Show servings of order to Customer | Completed Day 2
3 | PIX |  | Add pictures for better understanding | Completed Day 6
4 | CM |  | Be able to create a new manger for the owner | Completed Day 6
5 | P&L |  | Show proft/loss | Completed Day 7
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84